## RAID LOG
| RAID Log | Should you face any difficulty in completing the RAID Log, please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f | [8 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 3 | 1 | 1 | 0 | 0 | 0 | Instruction to use the RAID log template: • All fields must be duly filled • The descriptions for what to be filled in each of the fields are provided in the template. • Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes. • Understand what risks, assumptions, issues, and dependencies are from the description provided in the methodology document • Select the category of RAID from the dropdown menu provided in the “RAID category” field in the template. • Provide a valid description of the RAID category that you have selected in the “description” field provided. • Describe the impact the RAID category you have selected will have on the project in the “impact field”. • Describe how the impact of the selected RAID category can be reduced on the project in the “mitigation field” in the template. • Mention the responsible person for working on the selected RAID category in the “owner” field in the template. • Select the priority with which the selected RAID category needs to be mitigated. The following levels of priority are given in the drop-down menu. Select; o Negligible: if the RAID category is not going to make an impact on the project o Low: if the raid category is going to make very small impacts on the project o Moderate: if the RAID category is going to make a few impacts which can affect the project adversely. o High: if the RAID category is going to make major impacts on the project adversely. o Critical: if the raid category is going to affect the project at any stage. • Provide risk priority number based on the priority selected for the RAID category selected. • Select the status of the RAID category selected. Two options are provided in the drop-down menu. Select; o Open: if the responsible person is still working on the RAID category selected. o Closed: if the responsible person has worked on the RAID category and is solved.
| Project title: | Student Intern Success Analysis |  | Project Id: | IAC IP23 LP | Project Manager: | Harshada Topale |  |  | Assumption | 2 | 0 | 0 | 0 | 0 | 0
[10 empty] | Issue | 2 | 0 | 2 | 0 | 0 | 0
| DOCUMENT VERSION: |  |  | Last Updated date: | 2024-08-01 | Project Team Lead: | NA |  |  | Dependency | 2 | 0 | 0 | 1 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 9 |  |  |  |  | 5
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Student Data Includes Personal Information | Data Breach and Mishandling of Data Could Result in Ethical and Legal Issues | Comply With Privacy Regulations | Project Manager | Critical |  | Open | Risk
2 | Risk | Data Quality Issues | Inaccurate Analysis | Implement data validation and cleaning processes | Project Manager | High |  | Closed | Assumption
3 | Risk | Stakeholder availability | Communication Issue May Arise | Schedule regular meetings and ensure clear communication | Project Manager | High |  | Open | Issue
4 | Assumption | Data provided is accurate | Project results may be inaccurate | Conduct data quality checks and validation before analysis | Project Manager | Moderate |  | Closed | Dependency
5 | Assumption | Access to other tools | Delays in analysis and visualization | These tools are commonly used in the department and are expected to be readily available. | Project Manager | Moderate |  | Closed
6 | Issue | Missing data in some records | Missing data can lead to incomplete analysis | Implement data cleaning processes to fill missing values appropriately | Project Manager | High |  | Open | Open
7 | Issue | Technical difficulties with Power BI | Technical issues with Power BI can hinder the creation of visualizations, resulting in delays and potential gaps in the data presentation. | Seek technical support from any Learning Platform | Project Manager | High |  | Open | Closed
8 | Dependency | Data access from various colleges | Without timely access to data from various colleges, the project cannot proceed with the planned analysis, leading to significant delays | Establish data sharing agreements early in the project and maintain regular communication with data providers to ensure timely access. | Project Manager | Moderate |  | Open
9 | Dependency | The project relies on data visualization tools to present results | Inability to access these tools would hinder the presentation of insights | Ensure access to preferred data visualization tools | Project Manager | Critical |  | Closed | Critical
10 | [8 empty] | High
11 | [8 empty] | Moderate
12 | [8 empty] | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24