## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | Data Analytics
INTERN NAME: | Aman Rajbhar
PROJECT NAME: | Student Intern Success Aanlysis
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | 2024-08-01
Purpose of Document
Lessons Learned Logs are used to capture and share knowledge about what has worked well and what could have been done differently during the planning, management and delivery of an improvement project.
They help others learn from the project team's experience. Lesson Learned Logs: Help support a learning culture.
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments may be added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled
5. The descriptions for what to be filled in each of the fields are provided in the template.
6. Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | Student Intern Success Analysis |  |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT ID | IAC IP23
PROJECT MANAGER | Harshada Topale
PROJECT SPONSOR | Tushar Topale
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
| MENTION THE DATE ON WHICH THE MATTER WAS RAISED | DESCRIBE THE EVENT THAT WAS RAISED | MENTION WHICH CATEGORY THE EVENT WAS RELATED TO | MENTION YES OR NO | MENTION THE RECOMMENDATIONS THAT WAS SUGGESTED FOR SOLVING THE EVENT IF ANY | MENTION THE ACTION SELECTED FOR SOLVING THE VENT | MENTION THE RESPONSIBLE PERSON FOR SOLVING THE EVENT | SOLVED/ PENDING | MENTION IF ANYTHING ELSE OCCURRED DURING THE TIME OF THE MENTIONED EVENT
1 | 2024-07-26 | Data quality issues | Data Management | Yes | Implement comprehensive data validation and cleaning processes early | Conduct thorough data validation and cleaning before analysis begins | Self | Solved | Developing standardized data cleaning protocols
2 | 2024-07-26 | Technical difficulties with Power BI | Technical Challenges | Yes | Provide training sessions and seek technical support as needed |  | Self | Solved | Exploring alternative tools as backup
3 | 2024-07-27 | Missing data in records | Data Management | Yes | Implement data cleaning and imputation methods | Develop and apply data cleaning scripts; review data quality regularly | Self | Solved | Improved data validation process for future projects
4 | 2024-07-28 | Analysis and Visualization | Data Analysis and Visualization | No | Plan for iterative cycles in analysis and visualization to accommodate stakeholder feedback and ensure visualizations effectively convey insights. | Integrated documentation milestones with Power BI Query Editor to maintain transparency and facilitate version control. | Self | Solved | Conducted iterative data analysis Using Power BI.
5 | 2024-07-29 | Documentation Integration | Project Documentation | Yes | Integrate documentation milestones with analysis phases from the project's outset. Ensure consistent updates to documentation throughout the project to avoid last-minute rushes and discrepancies. | Documented Power BI File and methodologiess. | Self | Solved | Ensured consistency Power BI Visualization analysis outputs, and documentation formats throughout the project lifecycle.
6 | 2024-07-25 | Stakeholder availability | Communication | No | Establish regular communication channels with stakeholders to gather feedback early and often. Ensure presentations and demos are rehearsed thoroughly to align with stakeholder expectations and facilitate clear, concise delivery of findings. | Prepared presentation materials using Power BI tools. | Harshada Topale | Solved | Improved stakeholder engagement and communication